## MVP Features
Feature | Priority | Status | Week | Owner | Notes
CSV Upload & Parser | P0 | Not Started | 1-2 | Ahmad | Supports Business Reports, Active Listings, Account Health, Ads, FBA Inventory
AWS S3 File Storage | P0 | Not Started | 1-2 | Ahmad | Store uploaded CSVs securely
AWS Cognito Auth | P0 | Not Started | 1-2 | Ahmad | Sign up, login, JWT tokens
RDS PostgreSQL Setup | P0 | Not Started | 1-2 | Ahmad | Users, reports, audits, snapshots tables
FastAPI + Lambda Core | P0 | Not Started | 1-2 | Ahmad | API routes with Mangum adapter
API Gateway Setup | P0 | Not Started | 1-2 | Ahmad | HTTP endpoint with Cognito authorizer
Next.js Dashboard UI | P0 | Not Started | 2-3 | Ahmad | Tailwind + Headless UI components
Listing Health Scoring | P0 | Not Started | 3-4 | Ahmad | Title, bullets, images, Buy Box %
Account Health Scoring | P0 | Not Started | 3-4 | Ahmad | ODR <1%, Late Shipment <4%, Cancellation <2.5%
Traffic & Conversion Scoring | P0 | Not Started | 3-4 | Ahmad | High sessions + low conversion = listing issue
Ad Efficiency Scoring | P0 | Not Started | 3-4 | Ahmad | ACoS benchmarked, wasted spend flagged
Perplexity API Integration | P1 | Not Started | 5-6 | Ahmad | URL research mode for live competitor analysis
Dashboard Charts & Visuals | P1 | Not Started | 5-6 | Ahmad | Recharts: bar charts, gauges, trend lines
AI Recommendations Engine | P1 | Not Started | 7-8 | Ahmad | Plain-English action items per flagged issue
Audit Report PDF Export | P1 | Not Started | 7-8 | Ahmad | Shareable report with before/after tracking
Before/After Snapshots | P1 | Not Started | 7-8 | Ahmad | Store historical audits for progress tracking
Mobile Responsive UI | P2 | Not Started | 9-10 | Ahmad | Works on tablets and phones
PRD Documentation | P0 | Not Started | 9-10 | Ahmad | Required deliverable per offer letter
Loom Demo Walkthrough | P0 | Not Started | 10 | Ahmad | Required deliverable per offer letter
Deployment & Testing | P0 | Not Started | 10-12 | Ahmad | Vercel frontend + AWS backend live

## Tech Stack
Layer | Technology | Purpose | Cost (MVP)
Frontend | Next.js 14 (App Router) | React framework with file upload support | $0 (Vercel free tier)
UI Components | Tailwind CSS + Headless UI | Pre-built dashboard components | $0 (open source)
Charts | Recharts | Audit score visualizations | $0 (open source)
Auth | AWS Cognito | User sign-up, login, JWT validation | $0 (50k MAU free)
API Gateway | AWS API Gateway | HTTP endpoint for Lambda | $0 (1M requests free)
Backend | FastAPI + Mangum | Python API framework + Lambda adapter | $0
Compute | AWS Lambda | Serverless function execution | $0 (1M requests free)
File Storage | AWS S3 | Store uploaded CSV reports | $0 (5GB free)
Database | AWS RDS PostgreSQL | Relational DB for audits & users | $0 (750 hrs free)
Secrets | AWS Secrets Manager | Secure Perplexity API key storage | $0.40/month (1 secret)
CSV Parsing | Pandas | Parse Amazon flat-file reports | $0 (open source)
AI Research | Perplexity API (sonar-pro) | Live URL research mode | $5/1000 requests
Monitoring | AWS CloudWatch | Logs and Lambda metrics | $0 (5GB logs free)
Hosting | Vercel | Next.js frontend deployment | $0 (free tier)
Total Monthly Cost |  |  | ~$5-10 at MVP scale

## Week-by-Week Roadmap
Week | Phase | Deliverables | Success Criteria
1-2 | Foundation & Setup | AWS account setup, Cognito User Pool, RDS instance, S3 bucket, API Gateway, Lambda scaffolding, Next.js project init, Amplify auth integration | User can sign up and login. File upload UI renders. Lambda responds to /health check.
3-4 | CSV Parsing & Scoring Engine | Pandas parsers for 5 report types (Business, Listings, Account Health, Ads, FBA). Build 4 scoring modules: Listing Health, Account Health, Traffic/Conversion, Ad Efficiency. Store results in RDS. | Upload any Amazon CSV → app parses it correctly. Dashboard shows 0-100 audit score with color coding (green/yellow/red). Flags appear per ASIN with severity tags.
5-6 | Perplexity URL Research & Visuals | Integrate Perplexity API in Lambda. Build prompt template for URL research (competitor pricing, review sentiment, keyword gaps, BSR). Render Recharts: bar charts, gauges, trend lines on dashboard. | Paste Amazon product URL → app returns live competitive analysis card. Charts render for uploaded reports showing score breakdown and top/bottom ASINs.
7-8 | Recommendations & Export | AI recommendation templates keyed to each flag type (low Buy Box → pricing fix, high ODR → fulfillment review). PDF/CSV export with audit summary. Before/after snapshot storage in RDS. | Each flagged issue has plain-English action item. Export button generates downloadable PDF report. Audit snapshots stored so user can compare Week 1 vs Week 8.
9-10 | Polish & Documentation | Mobile-responsive design pass. Write PRD covering scope, features, data model, API routes. Record Loom walkthrough demo (5-10 min) showing upload → scoring → research → export flow. | App works on mobile/tablet. PRD document complete with screenshots. Loom video uploaded and shareable link ready.
10-12 | Testing & Deployment | Stress test with real Amazon report files (5+ different sellers). Deploy to Vercel production. API Gateway in prod mode. Setup CloudWatch alarms for Lambda errors. GitHub repo cleaned and documented. | App handles edge cases (malformed CSVs, missing columns). Live at custom domain. No errors in CloudWatch logs. GitHub README has setup instructions.

## Data Flow
Step | User Action | Frontend (Vercel) | Backend (AWS) | Result
1 | Sign up / Login | Amplify JS calls Cognito | Cognito issues JWT token | User authenticated, token stored
2 | Upload CSV | Next.js sends file + token to API Gateway | API Gateway validates JWT → Lambda receives file → stores in S3 → Pandas parses → saves to RDS | Raw file in S3, parsed data in RDS
3 | View Audit | Dashboard fetches audit results | Lambda queries RDS → returns scores, flags, ASINs | Dashboard renders charts + flagged issues
4 | Paste Amazon URL | Next.js sends URL + token to /research endpoint | Lambda calls Perplexity API with structured prompt → returns competitive analysis | Live research card displayed
5 | Export Report | User clicks Export PDF | Lambda queries RDS → generates PDF with all audit data | PDF downloads to user's device
6 | View History | Dashboard shows past audits | Lambda queries RDS snapshots table | Before/after comparison visible

## Amazon Reports Supported
Report Name | Download Location | Key Columns Parsed | What It Audits
Business Report (Detail Page Sales & Traffic) | Reports → Business Reports | Sessions, Page Views, Buy Box %, Conversion Rate, Units Ordered, Units Refunded | Traffic quality, conversion rates, Buy Box performance
Active Listings Report | Inventory → Inventory Reports → Active Listings | SKU, ASIN, Title, Price, Quantity, Condition, Status | Listing completeness, suppressed ASINs, pricing gaps
Account Health Report | Performance → Account Health → Download | Order Defect Rate, Late Shipment Rate, Pre-Fulfillment Cancel Rate, Policy Violations | Suspension risk, compliance issues, account standing
Advertising Report | Reports → Advertising Reports → Sponsored Products | Campaign, ACoS, CPC, CTR, ROAS, Impressions, Spend | Ad efficiency, wasted spend, ROAS optimization
FBA Inventory Report | Reports → Fulfillment → Show More → All Inventory | SKU, FNSKU, Sellable Units, Unsellable Units, Stranded Inventory | Stock health, stranded inventory, storage fees

## Scoring Logic
Score Type | Input Data | Algorithm | Output
Listing Health Score (0-100) | Title length, bullet count, image count, A+ content, price, brand registry | Each criterion weighted: Title 20pts, Bullets 20pts, Images 20pts, A+ 20pts, Price set 10pts, Brand 10pts. Deduct points for missing elements. | Per-ASIN score. <60 = Red, 60-79 = Yellow, 80+ = Green
Account Health Score (0-100) | ODR, Late Shipment Rate, Cancel Rate, Policy Violations | Start at 100. ODR >0.5% → -20pts. Late Ship >2% → -15pts. Cancel >1% → -10pts. Each violation → -5pts. | Overall account score. <70 = Red (suspension risk), 70-89 = Yellow, 90+ = Green
Traffic & Conversion Score (0-100) | Sessions, Page Views, Units Ordered, Conversion Rate | Conversion Rate benchmarked vs category avg. High traffic + low conversion = listing issue. Score = (Actual CR / Expected CR) * 100 | Per-ASIN score. Flags ASINs with >1000 sessions but <5% CR
Ad Efficiency Score (0-100) | ACoS, ROAS, CTR, CPC | Target ACoS varies by category (typically 20-35%). Score = 100 - abs((Actual ACoS - Target ACoS) / Target * 100). Penalize CTR <0.3%. | Per-campaign score. ACoS >50% = Red, 35-50% = Yellow, <35% = Green

## Perplexity Prompt Template
Section | Prompt Text
System Context | You are an expert Amazon FBA analyst. Analyze the following Amazon product listing URL and provide actionable competitive intelligence for a seller audit.
URL Input | Product URL: {amazon_url}
Research Instructions | 1. LISTING QUALITY: Assess title, bullet points, images, A+ content, review count, star rating. Note any missing elements or compliance issues. 2. COMPETITIVE LANDSCAPE: Identify top 3-5 competitors in same category. Compare pricing, review count, BSR (Best Seller Rank). 3. REVIEW SENTIMENT: Summarize common themes in negative reviews (1-3 stars). What are customers complaining about? 4. KEYWORD GAPS: What high-value keywords do competitors rank for that this listing misses? 5. PRICING POSITION: Is this product priced competitively vs similar items? Flag if significantly higher/lower. 6. OPPORTUNITY SCORE: On a scale of 1-10, rate the optimization opportunity for this listing.
Output Format | Return structured JSON: {"listing_quality": {"title_score": 0-10, "images_score": 0-10, "review_score": 0-10}, "competitors": [{"name": "", "price": "", "bsr": ""}], "negative_themes": [], "keyword_gaps": [], "pricing_insight": "", "opportunity_score": 0-10}
Example Response | {"listing_quality": {"title_score": 7, "images_score": 9, "review_score": 6}, "competitors": [{"name": "Brand X Widget", "price": "$24.99", "bsr": "#3,245 in Home & Kitchen"}], "negative_themes": ["Packaging arrives damaged", "Smaller than expected"], "keyword_gaps": ["heavy duty", "rust proof"], "pricing_insight": "Priced 15% above nearest competitor — consider $22.99", "opportunity_score": 8}

## Database Schema (RDS)
Table | Columns | Purpose
users | id (UUID PK), cognito_user_id (string), email (string), created_at (timestamp) | Store user accounts linked to Cognito
reports | id (UUID PK), user_id (FK), report_type (enum: business, listings, account_health, ads, fba), s3_key (string), uploaded_at (timestamp) | Track uploaded CSV files
audits | id (UUID PK), report_id (FK), overall_score (int 0-100), listing_score (int), account_health_score (int), traffic_score (int), ad_score (int), created_at (timestamp) | Store audit results per report
asin_details | id (UUID PK), audit_id (FK), asin (string), title (string), buy_box_pct (float), conversion_rate (float), sessions (int), flags (JSONB), score (int) | Per-ASIN breakdown
url_research | id (UUID PK), user_id (FK), amazon_url (string), perplexity_response (JSONB), created_at (timestamp) | Store Perplexity live research results
snapshots | id (UUID PK), user_id (FK), audit_id (FK), snapshot_date (timestamp), overall_score (int) | Before/after tracking for progress comparison

## Milestones & Success Metrics
Milestone | Week | Definition of Done | KVS Success Criteria
Authentication Working | 2 | User can sign up, log in, and token validates at API Gateway | Demo: login flow works end-to-end
CSV Upload Functional | 4 | User uploads any Amazon CSV → parsed correctly → data in RDS | Demo: upload 5 different report types, all parse without errors
Audit Scores Rendered | 6 | Dashboard shows 0-100 scores with color coding and flagged issues per ASIN | Demo: uploaded report shows audit card with scores and at least 3 flagged issues
Perplexity URL Research Live | 6 | Paste Amazon URL → live competitive analysis appears within 10 seconds | Demo: paste 3 different product URLs, all return structured insights
PDF Export Works | 8 | Click Export → downloadable PDF with audit summary and recommendations | Demo: PDF includes overall score, top issues, and action items
PRD + Loom Demo Complete | 10 | PRD written, Loom video recorded showing full user flow | Shareable PRD doc + Loom link sent to KVS for review
Production Deployment | 12 | App live at custom domain, no errors in CloudWatch, GitHub repo clean | KVS team can access live app and test with real seller accounts